**RESEARCH ACTIVITIES AND MILESTONES DATE (ORIGINAL VS. NEW)**

***\*Please refer to the original Proposal***

Project Title:

Name of PI:

Original Project Duration: 1 January 2019 – 31 December 2020

1st Extension Due to COVID-19: 1 January 2019 – 31 March 2021 (3 Months)

2nd Extension Due to COVID-19: 1 January 2019 – 30 September 2021 (6 Months)

Extension request: 6 Months (1 January 2019 – 31 March 2022)

1. **Research Activity (Based on Original Proposal)**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **No.** | **Research Activities** | **Status** | **Original Date (Based on Proposal)** | **Proposed New Date** |
| 1. |  | Completed | 1 January 2019 – 30 June 2019 | No changes |
| 2. |  | Completed | 1 July 2019 – 30 September 2019 | No changes |
| 3. |  | On-going | 1 October 2019 – 31 January 2020 | 1 January 2019 – 31 May 2020 |
| 4. |  | On-going | 1 February 2020 – 31 July 2020 | 1 June 2020 – 31 December 2021 |
| 5. |  | On-going | 1 August 2020 – 31 December 2020 | 1 January 2021 – 31 March 2022 |

1. **Milestones (Based on Original Proposal)**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **No.** | **Milestones** | **Status** | **Original Date (Based on Proposal)** | **Proposed New Date** |
| 1. |  | Completed | June 2019 | No changes |
| 2. |  | On-going | January 2020 | March 2020 |
| 3. |  | On-going |  |  |
| 4. |  | On-going |  |  |
| 5. |  | On-going | December 2020 | March 2022 |